# Proposal for M&A Due Diligence and Post-Merger Integration Advisory Services

Prepared for Crestline Financial Holdings  |  June 2025

# Executive Summary

Meridian Advisory Group is pleased to present this proposal to Crestline Financial Holdings to support due diligence and post-merger integration planning in connection with its proposed acquisition of a regional lending platform. Our approach is designed to identify integration risk early, protect Day 1 readiness, and build a disciplined path to synergy capture.

# Engagement Objectives

- Conduct financial, operational, and technology due diligence on the target

- Identify integration risks and quantify synergy opportunities

- Develop a Day 1 and Day 100 integration plan

- Support governance, reporting, and communication throughout the transition

# Scope of Services

- Financial and operational due diligence workstream

- Technology and systems compatibility assessment

- Cultural and organizational assessment

- Synergy identification and quantification

- Integration Management Office (IMO) setup and governance

- Day 1 readiness planning

# Our Approach & Methodology

| Phase | Duration | Description |
| --- | --- | --- |
| Due Diligence | 4-6 weeks | Financial, operational, technology, and cultural diligence workstreams run in parallel; findings compiled into a consolidated risk and opportunity report. |
| Integration Planning | 4 weeks | Define target operating model, functional integration plans, synergy targets, and the Day 1 critical path. |
| Day 1 Readiness | 2-4 weeks (to close) | Finalize communication plans, systems cutover requirements, and contingency plans for close. |
| Post-Close Integration Execution | 12-24 weeks | IMO-led execution of functional integration plans, synergy tracking, and steering committee reporting. |

Our standard approach: Our standard approach to M&A integration separates 'Day 1' readiness (the minimum required for legal close and business continuity) from longer-term synergy capture, which is sequenced over 100 days and beyond. This separation prevents the common pitfall of over-engineering Day 1 requirements at the expense of the close timeline.

# Indicative Timeline

Due diligence typically runs 4-6 weeks. Integration planning begins in parallel once preliminary diligence findings are available. The full program, from diligence through post-close execution, typically spans 6-9 months depending on the actual close date and the complexity of systems integration.

# Proposed Team

- Engagement Partner (executive sponsor and escalation point)

- M&A Advisory Lead

- Financial Diligence Manager

- Technology Diligence Lead

- Change Management Lead

- IMO Program Manager

# Investment

Due diligence is billed as a fixed fee. Integration planning and post-close execution are billed on a retained monthly basis, scaled to the size of the IMO team required.

- Due Diligence (fixed fee): $400,000 - $550,000

- Integration Planning & Execution (monthly retainer): $150,000 - $220,000 / month

- Typical program duration: 6-9 months post-diligence

# Why Meridian Advisory Group

- Deep financial services M&A experience across regional and mid-market transactions

- A disciplined Day 1 / Day 100 separation that protects close timelines

- Established IMO governance and synergy-tracking frameworks

- A team that has run diligence and integration together, not as two disconnected engagements

# Relevant Experience

Our team most recently supported the integration of two mid-market financial services firms, identifying 18% in run-rate synergies beyond the original deal model and completing Day 1 readiness two weeks ahead of the original close date.