# Proposal for Enterprise Data Migration & Systems Modernization Services

Prepared for Harborview Retail Group  |  November 2025

# Executive Summary

Meridian Advisory Group is pleased to present this proposal to Harborview Retail Group for a comprehensive data migration and systems modernization engagement. This engagement will support the transition from legacy on-premise inventory and point-of-sale systems to a modern cloud-based platform, with a focus on data integrity, minimal business disruption, and building internal capability for the go-forward environment.

# Engagement Objectives

- Migrate core transactional and customer data from legacy systems to the new cloud platform without unplanned service disruption

- Establish data governance and quality standards for the go-forward environment

- Minimize downtime during cutover windows across all store regions

- Build internal capability for ongoing system administration and data stewardship

# Scope of Services

- Current-state data architecture and systems assessment

- Data mapping, cleansing, and quality remediation

- Migration strategy, sequencing, and runbook development

- Phased migration execution across test, pilot, and full cutover stages

- Post-migration validation and reconciliation

- Knowledge transfer and training for internal IT staff

# Our Approach & Methodology

| Phase | Duration | Description |
| --- | --- | --- |
| Discovery & Assessment | 2-3 weeks | Inventory existing systems and data sources; identify data quality issues and remediation needs. |
| Design & Planning | 3-4 weeks | Define target data model, mapping rules, migration sequencing, and rollback contingencies. |
| Build & Test | 4-6 weeks | Develop migration pipelines and execute test migrations in a non-production environment. |
| Pilot Migration | 2 weeks | Migrate a representative subset (one region or store cluster) to validate the approach at scale. |
| Full Migration & Cutover | 2-4 weeks | Execute full-scale migration in planned waves, with defined rollback criteria at each wave. |
| Stabilization & Knowledge Transfer | 2 weeks | Post-migration support, reconciliation reporting, and training for internal IT staff. |

Our standard approach: Our standard approach to data migration engagements follows a phased, wave-based methodology rather than a single 'big-bang' cutover. We prioritize a pilot migration on a limited scope before proceeding to full-scale rollout, and we build rollback criteria into every wave so that a failed validation check can be caught and reversed before it affects the broader environment.

# Indicative Timeline

The full program is expected to run approximately 16-20 weeks from kickoff to stabilization, depending on the number of legacy systems in scope and data volume. Store-region cutover waves will be scheduled around Harborview's operating calendar to avoid peak trading periods.

# Proposed Team

- Engagement Partner (executive sponsor and escalation point)

- Program Manager (day-to-day delivery oversight)

- Data Migration Lead

- Data Engineers (2-3, scaling with wave volume)

- Change Management Lead

- QA / Validation Analyst

# Investment

Fees are structured as a fixed fee for the Discovery and Design phases, followed by time-and-materials billing with a not-to-exceed cap for Build through Stabilization. Based on the current known scope, the illustrative total program investment is:

- Discovery & Design (fixed fee): $180,000 - $220,000

- Build through Stabilization (T&M, capped): $670,000 - $930,000

- Estimated total program investment: $850,000 - $1,150,000

# Why Meridian Advisory Group

- A proven, wave-based migration methodology built specifically to minimize retail operational disruption

- Deep experience with retail inventory, POS, and customer data structures

- Dedicated data quality and reconciliation tooling used across prior engagements

- A risk-managed, pilot-first approach that surfaces issues before they scale

# Relevant Experience

We recently completed a similar multi-region data migration for a national specialty retailer, transitioning over 40 million customer records and three years of transactional history to a cloud data warehouse with zero unplanned downtime during business hours.