# Proposal for Digital Transformation and Process Automation Advisory Services

Prepared for Lattice Manufacturing Co.  |  January 2026

# Executive Summary

Meridian Advisory Group is pleased to present this proposal to Lattice Manufacturing Co. to support a digital transformation initiative focused on automating core finance and supply chain processes and modernizing reporting capabilities across its manufacturing operations.

# Engagement Objectives

- Automate manual, paper- and spreadsheet-based finance and supply chain processes

- Reduce manual processing time and error rates in core transactional workflows

- Establish a scalable reporting and analytics layer for operational decision-making

- Build internal capability to sustain and extend automation over time

# Scope of Services

- Process assessment and automation opportunity prioritization

- Robotic process automation (RPA) and workflow tool implementation

- Integration with existing ERP and finance systems

- Reporting and dashboard development

- Change management and end-user training

# Our Approach & Methodology

| Phase | Duration | Description |
| --- | --- | --- |
| Process Assessment | 3 weeks | Map current-state processes, quantify manual effort and error rates, and prioritize automation candidates by effort and impact. |
| Solution Design | 3 weeks | Design target-state workflows, select automation tooling, and define integration points with existing systems. |
| Build & Pilot | 6 weeks | Build automations for top-priority processes and pilot with a single business unit or process family. |
| Scale & Rollout | 8-10 weeks | Roll out validated automations across remaining business units in planned waves. |
| Sustain & Optimize | 4 weeks initial, ongoing | Establish a center of excellence, monitoring, and a continuous improvement cadence. |

Our standard approach: Our standard approach prioritizes automation candidates using a simple effort-versus-impact framework, and we always pilot on a single process family before scaling. This lets us validate assumptions about volume, exception handling, and system stability before committing to a broader rollout.

# Indicative Timeline

The initial program is expected to run approximately 20-24 weeks from kickoff through initial scale rollout, followed by an ongoing sustain engagement to extend automation coverage and maintain the center of excellence.

# Proposed Team

- Engagement Partner (executive sponsor and escalation point)

- Automation Lead

- Business Process Analysts (2)

- Solution Architect

- Change Management Lead

# Investment

Fees are structured as a fixed fee for the Assessment and Design phases, with Build through Sustain billed on a milestone basis tied to automation go-lives.

- Process Assessment & Solution Design (fixed fee): $180,000 - $220,000

- Build, Pilot, Scale & Rollout (milestone-based): $470,000 - $680,000

- Estimated total initial program investment: $650,000 - $900,000

- Ongoing Sustain support available as a monthly retainer following go-live

# Why Meridian Advisory Group

- Manufacturing-sector process expertise across finance and supply chain functions

- A proven pilot-then-scale approach that reduces rollout risk

- A dedicated automation center-of-excellence model for long-term sustainment

- Integration experience across major ERP platforms common in manufacturing environments

# Relevant Experience

We recently helped a mid-size industrial manufacturer automate its accounts payable and procurement matching processes, reducing manual processing time by 65% and cutting exception rates by more than half within the first two quarters after go-live.